## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2185-swen-261-10-d-10d
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JY; 3/4/2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | JY; 3/4/2019
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | JY; 3/4/2019
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | JY; 3/4/2019
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | CL; 3/4 2019
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | CL; 3/4 2019
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | CL; 3/4 2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | CL; 3/4 2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | CL; 3/4 2019
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | TY; 3/4/2019 | Pass | JY; 3/29/2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | TY: 3/4/2019 | Pass | JY; 3/29/2019
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Fail | TY; 3/4/2019; any amount of players can join a game and move pieces | Pass | JY; 3/29/2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | TY; 3/4/2019 | Pass | JY; 3/29/2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | TY; 3/4/2019 | Pass | TY; 3/29/2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | TY; 3/4/2019 | Pass | TY; 3/29/2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | TY; 3/4/2019 | Pass | TY; 3/29/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Fail | TY; 3/4/2019; Player board is not changed for a player and it not correctly set up | Pass | TY; 3/29/2019
As a player I want to resign from a game so that I can either play another game or get off WebCheckers. | Given I am in a match when I click resign then I am put back to the home page and my opponent is put in the end game experience, alerted to the fact that I resigned. |  |  | Pass | JY; 3/29/2019
As a player I want my turn to end when someone has won so that both players can play another game or do something else. | Given I am playing against someone when I capture their last piece then the game will tell me I won and I will be able to exit. |  |  | Pass | JY; 3/29/2019
| Given I am playing against someone when they capture my last piece then the game will tell me I lost and I will be able to exit. |  |  | Pass | JY; 3/29/2019
| Given I am playing against someone when I click resign then I will be redirected to /home and my opponent will know I resigned. |  |  | Pass | TY; 3/29/2019
| Given I am playing against someone when they click resign then I will be told they resigned and I will be able to exit. |  |  | Pass | TY; 3/29/2019
As a Player, I want to move a single piece diagonally forward so that I can get a piece to the other side. | Given It is the player's turn when the player picks up a piece and moves it diagonally then I expect the move to be checked if it was a valid movement |  |  | Pass | CL; 4/1/2019
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Pass | CL; 4/1/2019
| Given The opponent's is waiting for their turn when it become their turn then I expect the opponent's view of the board to be updated |  |  | Pass | CL; 4/1/2019
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Pass | CL; 4/1/2019
As a Player I want to capture an opponent's pieces so that I can remove one of my opponent's pieces at once to get closer to winning the game. | Given It is the player's turn when the player picks up a piece and jumps an opponent's piece then I expect the move to be checked if it was a valid movement |  |  | Pass | RL; 4/1/2019
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Pass | RL; 4/1/2019
| Given The opponent's is waiting for their turn when it become their turn then I expect the opponent's view of the board to be updated |  |  | Pass | RL; 4/1/2019
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Pass | RL; 4/1/2019
As a Player, I want to end my turn after a valid move so that the opponent can make their move and continue the game. | Given I have not yet submitted my turn when press "Submit" then my turn will be posted to the server. |  |  | Pass | CL; 4/1/2019 | Pass | RL; 4/7/2019
| Given that I have submitted my turn to the server when I am waiting to receive validation for the turn then I expect my to receive validation for the turn. |  |  | Pass | CL; 4/1/2019 | Pass | RL; 4/7/2019
| Given that I have made the the appropriate moves when I could have (i.e. jumping a piece as opposed to making a simple move) when submit my turn to the server then I expect to be notified that my turn was valid. |  |  | Fail | CL; 4/1/2019; Turn Validation does not work correctly | Pass | RL; 4/7/2019
| Given that I have made the the appropriate moves when I could have not (i.e. jumping a piece as opposed to making a simple move) when submit my turn to the server then I expect to be notified that my turn was invalid. |  |  | Fail | CL; 4/1/2019; Turn Validation does not work correctly | Pass | RL; 4/7/2019
As a Player I want to drag-and drop my king pieces so that I can make a simple move to one adjacent square diagonally forward away from me or backward toward me. | Given It is the player's turn when the player picks up a king piece and moves it diagonally then I expect the move to be checked if it was a valid movement |  |  | Pass | TY; 4/1/2019
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Pass | TY; 4/1/2019
| Given The opponent's is waiting for their turn when it becomes their turn then I expect the opponent's view of the board to be updated |  |  | Pass | TY: 4/1/2019
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Pass | TY; 4/1/2019
As a Player I want to capture multiple pieces so that I can remove many of my opponent's pieces at once to get closer to winning the game. | Given It is the player's turn when the player picks up a single piece and jumps multiple opponent's pieces then I expect the move to be checked if it was a valid movement |  |  | Fail | RL; 4/1/2019; Does not allow for multiple jump, only single jump | Pass | RL; 4/7/2019
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Fail | RL; 4/1/2019; Since model is not updated, user's view cannot be updated | Pass | RL; 4/7/2019
| Given The opponent's is waiting for their turn when it becomes their turn then I expect the opponent's view of the board to be updated |  |  | Fail | RL; 4/1/2019; Since model is not updated, opponent's view cannot be updated | Pass | RL; 4/7/2019
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Fail | RL; 4/1/2019; Since opponent's view cannot is not updated, players cannot switch turns | Pass | RL; 4/7/2019
As a Player I want to drag-and drop my king pieces so that I can make a single jump move to capture an opponent’s piece diagonally to adjacent vacant dark square away from me or backward toward me. | Given It is the player's turn when the player picks up a king piece and moves it diagonally then I expect the move to be checked if it was a valid movement |  |  | Pass | TY; 4/1/2019
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Pass | TY; 4/1/2019
| Given The opponent's is waiting for their turn when it becomes their turn then I expect the opponent's view of the board to be updated |  |  | Pass | TY; 4/1/2019
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Pass | TY; 4/1/2019
As a Player I want to drag-and drop my king pieces so that I can make a multiple move with the same piece to capture opponent’s pieces by jumping from vacant dark square to vacant dark square diagonally forward away from me or backward toward me. | Given It is the player's turn when the player picks up a king piece and jumps multiple opponent's pieces then I expect the move to be checked if it was a valid movement |  |  | Fail | CL; 4/1/2019; Multiple jump does not work, therefore king cannot multiple jump
| Given The turn was validated when the server process the request then I expect user's view to be updated |  |  | Fail | CL; 4/1/2019; Since player cannot multiple jump with king, user's view cannot be updated
| Given The opponent's is waiting for their turn when it becomes their turn then I expect the opponent's view of the board to be updated |  |  | Fail | CL; 4/1/2019; Since player cannot multiple jump with king, opponents's view cannot be updated
| Given The opponent's view was updated when the player turn is set to the opponent then I expect the control of the game to go to the opponent to make their turn |  |  | Fail | CL; 4/1/2019; Since opponents view cannot be updated, the players cannot switch turns
As a Player, I want be able to take back a previous move so that I can move another piece or the same piece to another position. | Given I want to move a piece when I press the "Backup" button then I expect my piece to move back to its previous position. |  |  | Pass | JY; 4/1/2019
| Given I pressed the "Backup" button when I am waiting to receive feedback from the server then I expect the server to inform me if it was successfully moved back or not |  |  | Pass | JY; 4/1/2019
As a Player, I want to place a second piece on top of the piece in the king-row so that I can crown the opponent's piece to become a king. | Given I have a single piece when move that single piece to the furthest row opposite of me, on my opponent's side, then I expect my piece to have the abilities of a king piece |  |  | Pass | CL; 4/1/2019
| Given I have a single piece when move that single piece to the furthest row opposite of me, on my opponent's side, then I expect to be notified visually that my piece is now a king piece. |  |  | Pass | CL; 4/1/2019
As a Player, I want to play multiple games so that I can play with as many people as possible. | Given I have already joined a game when I click on another player's game then I want to join that player's game and continue playing my previous game.
Given I am playing multiple games when I click on one game I have already joined then I expect to be able to play that game.
As a Player not playing a game, I want to be able to choose a game to spectate from a list of games being played, so I can decide who I want to spectate. | Given I am not in a game and signed in when click on a player that is currently in a game then I expect view a game that is currently in session.
Given I am not in a game and signed in when click on a player that is not currently in a game then I expect to stay in the homepage.
Given I am not in a game and signed in when click on a player that is not currently in a game then I expect to be notified that I can't spectate that player because they are not in game.
As a Player not playing a game, I want to be able to enter Spectator Mode at anytime I am signed in so I can view other players' games. | Given that a player is playing a game when I choose to spectate them then I expect to view the game they are playing.
Given that I am currently spectating a player's game when try to play their game then to be unable to interact with their game.
Given that I am currently spectating a player's game when I join their game then I expect to be notified that I am only spectating their game.
As a Spectator, I want to be able to leave a game I am spectating so that I can spectate another game or play a game myself. | Given I am spectating another player's game when choose to stop spectating their game then I expect to stop spectating their game.
Given I am spectating another player's game when choose to stop spectating their game then I expect to be taken back to the home page.
As a Player, I want to replay my games so that I can study them and learn from them. | Given that I am not in Replay Mode when decide I want to be in replay mode then I expect to be in Replay mode.
Given that I am not in Replay Mode when I join replay mode then I expect to be notified I have joined replay mode.
As a Player, I want view the next turn or previous turn so that I can see how the game progressed and how to improve next time. | Given that I am replay mode when I click the "Next" button (to view the next turn that was made in a game) then I expect to see the next turn that was made in the game.
Given that I am replay mode when I click the "Previous" button (to view a previous turn that was made in a game) then I expect to see a previous turn that was made in the game.
As a Player, I want to stop replaying a game so that I can watch another replay, play another game, or do something else. | Given I am in replay mode when decide to the leave replay then I expect to leave replay mode.
Given I am in replay mode when decide to the leave replay then I expect to go back to the home page.
As a Player, I want know all my game options so that play, spectate or replay a game. | Given I have just signed in when I view the home page then I expect to have the option to spectate a player that is signed in.
Given I have just signed in when I view the home page then I expect to have the option to view replays of a previous game.